## Sheet1
Tasks | Breakdown | Who? | How long? (Hours)
Design
UML/Class diagrams |  | Sean | 8
Gantt chart |  | James | 1
Hacknplan |  | James | 1
Technical Docs |  | All | 3
Segment work |  | All | 1
Methodology |  | All | 0.5
Level design |  | James | 3
Wireframes |  | Jamie | 5
Character behaviour |  | James | 3
State diagrams |  | James | 3
Asset collection
Icons/UI/UX |  | Jamie | 1
Logo |  | All | 1
Title |  | All | 1
Sounds |  | Jamie | 1
Testing
Unit testing |  | All | 2
Black/White box testing |  | All | 2
Acceptance testing |  | All | 2
System testing |  | All | 2
Regression Testing |  | All | 2
Integration testing |  | All | 2
Development
Program to use |  | All | 0.5
Github |  | All | 0.5
Regular meetings |  | All | 40
Programming
Menus/UI/UX
| Titles | Jamie | 1
| Options | Jamie | 5
| Highscores | Jamie | 4
| Press back to quit | Jamie | 1
| Quests | Jamie | 4
| Background | Jamie | 2
| Sounds | Jamie | 2
Tutorial/Levels
| Multiple levels | Sean | 20
| Game hints | Sean | 3
| Themed | Sean | 1
Titles
| Space Tower Defence - STD | Sean | 1
Databases
| Software | James | 0.5
| Highscores | James | 2
| Names | James | 2
| Plan | James | 2
| Host | James | 4
| Integration | James | 8
Waves
| Pathfinding | Xavier | 2
| Difficulty | Xavier | 2
| Random placements of enemies | Xavier | 1
| Enemies | Xavier | 10
Damage system
| Health bars | Xavier | 1
| Option for value display | Xavier | 2
| splash/effects/plan abilities | Xavier | 4
Score
| Experience | Xavier | 1
Characters
| Heroes | All | 4
| Tower | All | 4
| Boss | All | 4
| Enemies | All | 4
Story
| Lore | All | 4
| Plan | All | 4
| Cutscenes/ message system | All | 5
| Total hours |  | 171.5
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.